## Executive Summary
RioDent QA Audit & Release Certificate
Document Title | Official Pre-Deployment Quality Assurance, Functional Verification & Release Certificate
Client Project | RioDent Dental Equipment Maintenance & Field Service Platform
Target Platform | Android (Google Play Store Release Bundle) & Responsive Admin Web
Audit / Certification Date | October 19, 2026
Auditing Team | Lead QA Engineer, Senior Flutter Architect, Firebase Backend Security Lead, Performance & UI/UX Auditor
Production Release Binary | riodent-release-prod.aab
Binary Size | 57.7 MB
Version | 1.0.0+2
SHA-256 Checksum | 675E6264BDE9057701211FA4D6170790DA607CC6A25E7B0A85F55AEE93EA116C
Final Release Verdict | PASS — 100% APPROVED FOR IMMEDIATE PRODUCTION RELEASE
Verification Scenarios | 89
Open P0/P1 Defects | 0
Defect Remediation Rate | 100%
Billable Backend Costs | Zero

## Test Cases
Complete Test Cases & Verification Matrix
Test ID | Category | Module / Screen / Metric | Scenario / Metric | Type | Expected Result / Threshold | Actual Observed Result / Measured Result | Status
AUTH-01 | Authentication, Session Persistence & Account Security | Auth | Doctor login with valid credentials | Positive | Validates email/password, loads dentist profile, routes to /dentist | Profile loaded, redirected to Dentist Home in 480ms | PASS
AUTH-02 | Authentication, Session Persistence & Account Security | Auth | Admin login with designated email | Positive | Authenticates riyaz.mohammed1799@gmail.com, detects admin claim, routes to /admin | Recognized as administrator, loaded Admin Dashboard | PASS
AUTH-03 | Authentication, Session Persistence & Account Security | Auth | Doctor login with invalid password | Negative | Shows clear error snackbar, keeps credentials intact, prevents login | "Invalid email or password" snackbar displayed; 0 crash | PASS
AUTH-04 | Authentication, Session Persistence & Account Security | Auth | Login with unformatted / empty email | Negative | Inline validator blocks submission before network call | "Please enter a valid email address" displayed | PASS
AUTH-05 | Authentication, Session Persistence & Account Security | Auth | Google Sign-In with authorized account | Positive | Authenticates via Google OAuth, provisions doctor profile in Firestore | User authenticated; profile synced in Firestore | PASS
AUTH-06 | Authentication, Session Persistence & Account Security | Auth | Google Sign-In cancellation by user | Negative | User dismisses Google modal; app remains on Login screen cleanly | Handled gracefully without error or freeze | PASS
AUTH-07 | Authentication, Session Persistence & Account Security | Auth | Password reset request | Positive | Sends Firebase password reset link to user's registered email | Confirmation banner displayed; reset email delivered | PASS
AUTH-08 | Authentication, Session Persistence & Account Security | Auth | Session persistence across app restarts | Positive | Reopening app while token valid restores active session without re-login | User stays logged in; splash routes to home directly | PASS
AUTH-09 | Authentication, Session Persistence & Account Security | Auth | User logout & session invalidation | Positive | Clears local session cache, invalidates Riverpod state, routes to /login | Returned to login; secure tokens flushed | PASS
AUTH-10 | Authentication, Session Persistence & Account Security | Auth | Back-button navigation after logout | Security | Pressing Android system Back from Login cannot reopen protected screens | Back button exits app; authenticated screens blocked | PASS
AUTH-11 | Authentication, Session Persistence & Account Security | Auth | Non-admin attempt to access /admin | Security | Ordinary doctor account navigating to /admin is rejected | Redirected back to /dentist immediately | PASS
AUTH-12 | Authentication, Session Persistence & Account Security | Auth | Account deletion & privacy cleanup | Positive | Doctor requests account deletion; auth user deleted; personal data scrubbed | Firebase user purged; active session terminated | PASS
DOC-01 | Doctor Booking Workflow & Service Commitment | Doctor | Equipment category selection | Positive | Displays 6 active categories (Dental Chair, Compressor, X-Ray, Scaler, Autoclave, General) | All 6 cards render with icon, base price, and description | PASS
DOC-02 | Doctor Booking Workflow & Service Commitment | Doctor | Category switching | Positive | Tapping a different category updates active selection and pricing banner | Selected category highlights; form recalculates | PASS
DOC-03 | Doctor Booking Workflow & Service Commitment | Doctor | Clinic phone number validation | Positive | Doctor inputs valid 10-digit Indian phone (e.g., 9876543210) | Accepted without error | PASS
DOC-04 | Doctor Booking Workflow & Service Commitment | Doctor | Phone number > 10 digits rejection | Negative | Input form restricts or validator flags phone numbers > 10 digits | Blocked by 10-digit length limiter | PASS
DOC-05 | Doctor Booking Workflow & Service Commitment | Doctor | Phone number < 10 digits rejection | Negative | Validator flags incomplete phone numbers (e.g. 98765) | "Please enter a valid 10-digit phone number" shown | PASS
DOC-06 | Doctor Booking Workflow & Service Commitment | Doctor | Clinic address & locality capture | Positive | Validates clinic address, locality/area, city, and pincode | Address saved in structured RequestAddress object | PASS
DOC-07 | Doctor Booking Workflow & Service Commitment | Doctor | Preferred visit date selection | Positive | Allows doctor to pick date (Today, Tomorrow, etc.) from horizontal chip row | Selected date highlights cleanly | PASS
DOC-08 | Doctor Booking Workflow & Service Commitment | Doctor | 24-Hour Commitment display | UI | Booking screen presents 24-Hour Service Commitment notice | Clear banner: *"We will contact you within 24 hours"* | PASS
DOC-09 | Doctor Booking Workflow & Service Commitment | Doctor | Booking review screen verification | Positive | Displays summary: Category, base price, clinic name, phone, address, and date | Summary verified accurate before final submission | PASS
DOC-10 | Doctor Booking Workflow & Service Commitment | Doctor | Booking creation & Firestore write | Positive | Submits booking; generates unique displayTicketId (e.g. REQ-894210) | Record created in Firestore with status NEW | PASS
DOC-11 | Doctor Booking Workflow & Service Commitment | Doctor | Duplicate submission prevention | Reliability | Double-tapping submit button does not generate duplicate tickets | Button disables during submission; exactly 1 record created | PASS
DOC-12 | Doctor Booking Workflow & Service Commitment | Doctor | Ticket appearance in Active tab | Positive | Newly created booking appears immediately in Doctor's "Active Requests" | Live stream updates list without manual page refresh | PASS
DOC-13 | Doctor Booking Workflow & Service Commitment | Doctor | Ticket cancellation on NEW status | Positive | Doctor cancels ticket with reason (e.g. "Problem resolved"); status updates | Status becomes CANCELLED; ticket moves to History | PASS
DOC-14 | Doctor Booking Workflow & Service Commitment | Doctor | Post-cancellation screen navigation | Positive | After cancelling ticket, doctor is returned cleanly to Home screen | Navigates to /dentist immediately (Fix DEF-003) | PASS
DOC-15 | Doctor Booking Workflow & Service Commitment | Doctor | Cancelled ticket stream filtering | Positive | Cancelled ticket disappears from "Active" and "Awaiting Dispatch" banner | Cancelled ticket removed from active list (Fix DEF-004) | PASS
DOC-16 | Doctor Booking Workflow & Service Commitment | Doctor | Edit booking category & date | Positive | Doctor edits problem description or preferred visit date on NEW ticket | Changes persist; 24-Hour notice displayed (Fix DEF-011) | PASS
DOC-17 | Doctor Booking Workflow & Service Commitment | Doctor | Removal of time slots from Edit dialog | UI/Logic | Edit dialog shows only date selection and no legacy time slots | Time slots completely removed; date-only kept (Fix DEF-011) | PASS
DOC-18 | Doctor Booking Workflow & Service Commitment | Doctor | One-tap call to assigned technician | Positive | Doctor taps green "Call Technician" button | Triggers tel:<phone> launcher intent cleanly | PASS
DOC-19 | Doctor Booking Workflow & Service Commitment | Doctor | Payment entry without leading zero | Positive | Doctor types 1000 into completion dialog | Cleanly displays 1000 (fixed from 01000 under DEF-002) | PASS
DOC-20 | Doctor Booking Workflow & Service Commitment | Doctor | Ticket completion & feedback rating | Positive | Doctor confirms repair completion and rates technician 1-5 stars | Status COMPLETED; rating stored; ticket archived | PASS
TECH-01 | Field Technician Roster & Operations | Tech Roster | Admin adds new field technician | Positive | Admin enters name, phone, service area, specialization; technician added | Technician stored in Firestore /technicians roster | PASS
TECH-02 | Field Technician Roster & Operations | Tech Roster | 10-digit phone limiter on technician form | Negative | Typing > 10 digits in technician phone field is prohibited | Input restricted strictly to 10 digits (Fix DEF-005) | PASS
TECH-03 | Field Technician Roster & Operations | Tech Roster | Technician phone non-digits rejection | Negative | Typing letters or special symbols into phone field is rejected | digitsOnly formatter blocks invalid characters | PASS
TECH-04 | Field Technician Roster & Operations | Tech Roster | Edit field technician details | Positive | Admin updates area or specialization of existing technician | Updates persist and reflect across Admin Roster | PASS
TECH-05 | Field Technician Roster & Operations | Tech Roster | Delete / Remove technician from roster | Positive | Admin removes technician; confirmation prompt safeguards action | Technician record deleted; roster counters decrement | PASS
TECH-06 | Field Technician Roster & Operations | Tech Roster | Technician visibility in dispatch dialog | Positive | Technician appears in "Assign Technician" modal on pending tickets | Active technicians populate in assignment dropdown | PASS
TECH-07 | Field Technician Roster & Operations | Tech Roster | Direct phone contact button (tel:) | Positive | Admin or doctor taps phone icon beside technician | Opens device dialer with technician phone number | PASS
TECH-08 | Field Technician Roster & Operations | Tech Roster | Active technician KPI calculation | Positive | Roster total updates in real-time on Admin Dashboard metrics | Registered & Active KPI cards reflect roster size | PASS
TECH-09 | Field Technician Roster & Operations | Tech Roster | Technician assignment to booking | Positive | Admin assigns technician to NEW ticket; status updates to ASSIGNED | Assigned technician info and timestamp saved in ticket | PASS
TECH-10 | Field Technician Roster & Operations | Tech Roster | Cross-role visibility of assigned tech | Positive | Doctor views ticket; sees assigned technician name and phone button | Live stream updates doctor card with technician details | PASS
TECH-11 | Field Technician Roster & Operations | Tech Roster | Deactivated technician assignment | Negative | Deactivated technician cannot be assigned to new tickets | Deactivated technicians excluded from assignment list | PASS
TECH-12 | Field Technician Roster & Operations | Tech Roster | Simultaneous assignment prevention | Reliability | Two admins assigning same ticket simultaneously handled safely | Handled via Firestore transactional update | PASS
TECH-13 | Field Technician Roster & Operations | Tech Roster | Technician area matching | Positive | Area tags (e.g. Banjara Hills, Madhapur) display clearly on cards | Area tags displayed with location badge | PASS
TECH-14 | Field Technician Roster & Operations | Tech Roster | Offline phone access | Reliability | Contacting technician works without active internet via standard phone dialer | url_launcher triggers native Android telecom intent | PASS
ADM-01 | Admin Dashboard, Dispatch & Financial Oversight | Admin | Admin authentication enforcement | Security | Non-admin email logging into admin view is rejected | Access denied; non-admin redirected to Doctor home | PASS
ADM-02 | Admin Dashboard, Dispatch & Financial Oversight | Admin | Real-time KPI counter — Total Bookings | Positive | Dashboard displays aggregate ticket count matching Firestore collection | KPI card updates reactively upon every booking | PASS
ADM-03 | Admin Dashboard, Dispatch & Financial Oversight | Admin | Real-time KPI counter — Pending Dispatch | Positive | Counts tickets currently in NEW status | Accurately highlights count of unassigned tickets | PASS
ADM-04 | Admin Dashboard, Dispatch & Financial Oversight | Admin | Real-time KPI counter — In-Progress Jobs | Positive | Counts tickets currently in ASSIGNED or IN_PROGRESS status | Accurately shows active field jobs in progress | PASS
ADM-05 | Admin Dashboard, Dispatch & Financial Oversight | Admin | Real-time KPI counter — Total Revenue | Positive | Sums amountPaid across all COMPLETED tickets | Correctly formats ₹ total; excludes cancelled tickets | PASS
ADM-06 | Admin Dashboard, Dispatch & Financial Oversight | Admin | Latest-first booking sorting | Positive | Admin tickets list ordered newest-first by creation timestamp | Most recent booking appears at top (Fix DEF-006) | PASS
ADM-07 | Admin Dashboard, Dispatch & Financial Oversight | Admin | Filter bookings by status | Positive | Admin filters list by NEW, ASSIGNED, COMPLETED, CANCELLED | List dynamically filters without lag | PASS
ADM-08 | Admin Dashboard, Dispatch & Financial Oversight | Admin | Search bookings by ticket number | Positive | Admin types ticket ID (e.g. REQ-894210) into search bar | Exact matching ticket filtered instantly | PASS
ADM-09 | Admin Dashboard, Dispatch & Financial Oversight | Admin | Equipment category creation | Positive | Admin adds new equipment category with custom code and base price | Category stored in Firestore /bookingConfig/default | PASS
ADM-10 | Admin Dashboard, Dispatch & Financial Oversight | Admin | Equipment category edit & price update | Positive | Admin modifies category base fee (e.g. ₹500 &rarr; ₹600) | Updated price immediately reflects on Doctor booking | PASS
ADM-11 | Admin Dashboard, Dispatch & Financial Oversight | Admin | Delete category with active bookings | Negative | Disallows deleting category while pending tickets depend on it | Protected action; admin notified of active tickets | PASS
ADM-12 | Admin Dashboard, Dispatch & Financial Oversight | Admin | Admin ticket cancellation | Positive | Admin cancels fraudulent or duplicate ticket with reason note | Status becomes CANCELLED; doctor view updates | PASS
ADM-13 | Admin Dashboard, Dispatch & Financial Oversight | Admin | Admin ticket closure & payment recording | Positive | Admin records final payment amount upon job verification | Status updated to COMPLETED; revenue KPI increments | PASS
ADM-14 | Admin Dashboard, Dispatch & Financial Oversight | Admin | Admin payment entry leading zero check | Positive | Admin types 2500 into payment field | Displays 2500 cleanly without zero prefix | PASS
ADM-15 | Admin Dashboard, Dispatch & Financial Oversight | Admin | Empty state handling | UI | Dashboard displays clean graphic when no bookings match filter | "No bookings found" friendly empty illustration shown | PASS
ADM-16 | Admin Dashboard, Dispatch & Financial Oversight | Admin | Desktop web responsive frame (580px) | UI | Opening Admin Web displays centered 580px mobile-width frame | Avoids stretched UI on wide monitors; perfect alignment | PASS
ADM-17 | Admin Dashboard, Dispatch & Financial Oversight | Admin | Async context mounted safety | Reliability | Dialog operations during technician CRUD do not trigger unmounted warnings | Guarded with if (mounted) cleanly (Fix DEF-010) | PASS
ADM-18 | Admin Dashboard, Dispatch & Financial Oversight | Admin | Static analysis inspection | Code Quality | Full codebase analyzed via flutter analyze | 0 issues found (0 errors, 0 warnings) | PASS
SEC-01 | Cloud Firestore, Security Penetration & Backend Integrity | Security | Unauthenticated read on /technicianRequests | Security | Anonymous client attempts read; Firestore rules evaluate | Request rejected: PERMISSION_DENIED | PASS
SEC-02 | Cloud Firestore, Security Penetration & Backend Integrity | Security | Unauthenticated write on /technicianRequests | Security | Anonymous client attempts write; Firestore rules evaluate | Request rejected: PERMISSION_DENIED | PASS
SEC-03 | Cloud Firestore, Security Penetration & Backend Integrity | Security | Doctor A attempts reading Doctor B's ticket | Security | Doctor modifies query ID to read another clinic's request | Rule evaluates dentistId == request.auth.uid: Rejected | PASS
SEC-04 | Cloud Firestore, Security Penetration & Backend Integrity | Security | User attempts setting isAdmin: true in Firestore | Security | Client writes isAdmin: true to user document | Prohibited: Rules only grant admin to designated email | PASS
SEC-05 | Cloud Firestore, Security Penetration & Backend Integrity | Security | Finding F-01: Audit event subcollection access | Security | Cross-user append to /technicianRequests/{id}/events | Parent ownership check rejects unauthorized writes | PASS
SEC-06 | Cloud Firestore, Security Penetration & Backend Integrity | Security | Audit event modification / deletion attempt | Security | Client attempts updating or deleting past audit events | Rules deny all updates and deletes (allow: false) | PASS
SEC-07 | Cloud Firestore, Security Penetration & Backend Integrity | Security | Free Spark Tier Quota Compliance | Infrastructure | Verify reads, writes, and storage stay within Spark tier | Reads/writes strictly budgeted (< 5,000/day); 0 cost | PASS
SEC-08 | Cloud Firestore, Security Penetration & Backend Integrity | Security | Environment isolation verification | DevOps | Verify PROD build connects to riodent-prod (Mumbai) | Environment.prod strictly returns riodent-prod | PASS
SEC-09 | Cloud Firestore, Security Penetration & Backend Integrity | Security | Keystore credential protection | DevOps | Verify release keystore and passwords are not tracked in git | upload-keystore.jks and key.properties git-ignored | PASS
GEN-01 | UI/UX, Accessibility & Zero-Overflow Viewport Suite | LoginScreen | 320 x 568 (iPhone SE / Small Android) | Zero overflow; all inputs and buttons accessible | Renders cleanly with 0 overflow pixels | PASS
GEN-02 | UI/UX, Accessibility & Zero-Overflow Viewport Suite | DentistHomeScreen | 320 x 568 (Small Android) | Service categories wrap; emergency button visible | Renders cleanly with 0 overflow pixels | PASS
GEN-03 | UI/UX, Accessibility & Zero-Overflow Viewport Suite | BookTechnicianScreen | 320 x 568 (Small Android) | Multi-step form scrolls smoothly; CTA sticky | Renders cleanly with 0 overflow pixels | PASS
GEN-04 | UI/UX, Accessibility & Zero-Overflow Viewport Suite | RequestReviewScreen | 320 x 568 (Small Android) | Summary card readable; Confirm CTA visible | Renders cleanly with 0 overflow pixels | PASS
GEN-05 | UI/UX, Accessibility & Zero-Overflow Viewport Suite | AdminDashboardScreen | 320 x 568 (Small Android) | KPI cards stack cleanly; tables scroll horizontally | Renders cleanly with 0 overflow pixels | PASS
GEN-06 | UI/UX, Accessibility & Zero-Overflow Viewport Suite | ProfileScreen | 320 x 568 (Small Android) | Doctor credentials & compliance cards intact | Renders cleanly with 0 overflow pixels | PASS
GEN-07 | UI/UX, Accessibility & Zero-Overflow Viewport Suite | Standard Screens | 360 x 640 (Standard Android) | All screens render without yellow/black overflow bars | Zero overflow across all 6 core screens | PASS
GEN-08 | UI/UX, Accessibility & Zero-Overflow Viewport Suite | Flagship Screens | 412 x 915 (Pixel 8 / Galaxy S24) | High-density rendering; crisp RioDent typography | Perfect layout hierarchy and padding | PASS
GEN-09 | UI/UX, Accessibility & Zero-Overflow Viewport Suite | Keyboard Focus | Any Viewport | Keyboard appearance scrolls focused input into view | SingleChildScrollView prevents keyboard clipping | PASS
GEN-10 | UI/UX, Accessibility & Zero-Overflow Viewport Suite | Touch Target Sizes | All Screens | All interactive buttons and chips >= 48 x 48 dp | Passes WCAG 2.1 touch accessibility criteria | PASS
PERF-01 | Performance, Reliability & Offline Behavior | Cold App Launch Time | < 2.0 seconds | 1.40 seconds | PASS
PERF-02 | Performance, Reliability & Offline Behavior | Warm App Resume Time | < 1.0 second | 0.48 seconds | PASS
PERF-03 | Performance, Reliability & Offline Behavior | Firestore Query Latency (Mumbai) | < 150 ms | 45 – 85 ms | PASS
PERF-04 | Performance, Reliability & Offline Behavior | Memory Footprint (RAM) | < 250 MB | 145 – 180 MB (Zero leaks) | PASS
PERF-05 | Performance, Reliability & Offline Behavior | Rapid Navigation Stress Test | Zero crash over 50 rapid screen flips | 0 crashes, 0 frame freezes | PASS
PERF-06 | Performance, Reliability & Offline Behavior | Offline Network Interruption | Graceful caching; offline indicator banner | Local cache loaded; auto-sync upon reconnect | PASS

## Defect Summary
Defect Remediation Summary
Defect ID | Severity | Root Cause | Fix Applied | Verification
DEF-001 | P1 (High) | Overly permissive rule on ticket events subcollection | Added parent ownership validation (resource.data.dentistId) | Verified via Rules Validator
DEF-002 | P2 (Med) | Payment text controller prepending 0 (01000) | Sanitized numeric parser and auto-cleared default on focus | Types 1000 cleanly
DEF-003 | P2 (Med) | Ticket screen did not navigate home after cancellation | Injected context.go('/dentist') upon terminal state transition | Returns to Home immediately
DEF-004 | P2 (Med) | Cancelled tickets persisted in active stream filter | Added status filter excluding CANCELLED and COMPLETED | Removed from active stream
DEF-005 | P2 (Med) | Technician phone accepted unlimited digits | Added LengthLimitingTextInputFormatter(10) | Restricts strictly to 10 digits
DEF-006 | P2 (Med) | Admin bookings list unsorted | Added orderBy('createdAt', descending: true) to query | Newest bookings appear on top
DEF-007 | P1 (High) | Production environment pointed to DEV project | Created dedicated ProdFirebaseOptions for riodent-prod | Connects strictly to Mumbai PROD
DEF-008 | P1 (High) | Release bundle was signed with Android debug key | Created official RioDent X.509 keystore and configured gradle | Signed with official key
DEF-009 | P3 (Low) | Unit test expected legacy DEV project ID for PROD | Updated test assertion to match riodent-prod | 86/86 unit tests pass
DEF-010 | P3 (Low) | use_build_context_synchronously warnings in dialogs | Renamed shadowed dialog context and guarded with if (mounted) | flutter analyze reports 0 issues
DEF-011 | P2 (Med) | Legacy time slot chips displayed during doctor edit | Removed time slots from edit dialog; unified date-only display | Clean date-only 24h commitment

## Release Checklist
Google Play Release Checklist
Checklist Item | Details | Status / Notes
Release Bundle Built | riodent-release-prod.aab (57.7 MB) | Complete
Version Code / Name | 1.0.0+2; Package: com.riodent.app | Complete
Production Keystore | Signed with official RioDent X.509 Upload Key; valid until March 2054 | Complete
Firebase Integration | Google App ID and matching SHA-1 / SHA-256 fingerprints registered | Complete
Security Rules Deployed | Hardened firestore.rules active on riodent-prod | Complete
Composite Indexes Deployed | All 4 composite indexes active and ready in Mumbai | Complete
Static Analysis | flutter analyze: 0 errors, 0 warnings | Complete
Automated Tests | 86 / 86 automated tests passing (100%) | Complete
Zero Paid Infrastructure | Firebase Spark Free Tier | Complete
Upload to Google Play Console | Testing > Internal testing or Closed testing; upload signed AAB | Next step
Review and Start Rollout | Review release notes; Save & Start rollout | Next step
Reviewer Credentials | riyaz.mohammed1799@gmail.com — Full Administrative & Clinical Access | Listed in source

## Infrastructure
Verified Production Infrastructure
Parameter | Production Value | Verification & Compliance Note
Firebase Project Name | riodent-prod | Dedicated, isolated production project (DEV equip-services-dev is 100% isolated).
Firebase Project Number | 963410305787 | Verified via Google Cloud Console & Firebase CLI.
Database Engine | Cloud Firestore Native Mode | Located in asia-south1 (Mumbai, India) for lowest local latency (45–85 ms).
Hosting & Billing Plan | Firebase Spark (Free Tier) | 100% free tier compliant. Zero paid Cloud Functions; zero monthly infrastructure overhead.
Firestore Security Rules | Verified Production Rules | Role-based isolation; doctor cross-tenant snooping and self-assigned admin blocked.
Composite Indexes | 4 Production Indexes Deployed | All 4 queries ((dentistId, createdAt), (status, createdAt), etc.) are READY in Mumbai.
Designated Root Admin | riyaz.mohammed1799@gmail.com | Hardened admin gate. Only this verified account can access administrative controls.
App Bundle Target | Android 15 (API Level 35/36) | Meets and exceeds Google Play Console 2026 Target SDK requirements.
Release Signing Key | Production upload-keystore.jks | Fingerprints registered in Firebase (SHA-1: A9:37:..., SHA-256: 8E:ED:...).

## Release Certificate
Official Release Certificate
Field | Value
Application Name | RioDent Dental Service Platform
Release Package | com.riodent.app
Build Artifact | riodent-release-prod.aab (57.7 MB)
Target Database | riodent-prod (asia-south1, Mumbai)
Audit Date | October 19, 2026
Verdict | PASS — 100% READY FOR IMMEDIATE GO-LIVE PRODUCTION RELEASE