## Overview
RioDent MVP - QA Test Plan v2
Updated for: Google-first sign-up, no phone OTP, no images, Hyderabad-only address, time slots, doctor-closes-with-amount, cancel reasons, admin dashboard, 1 lakh scale, Firebase prod release.
Execution dashboard (updates from the Status column in 'Test Cases')
Module | Total | Pass | Fail | Blocked | Not Run | % Pass
Auth - Doctor | 24 | 0 | 0 | 0 | 24 | 0%
Auth - Admin | 11 | 0 | 0 | 0 | 11 | 0%
Profile | 6 | 0 | 0 | 0 | 6 | 0%
Doctor - Home | 10 | 0 | 0 | 0 | 10 | 0%
Doctor - Booking | 35 | 0 | 0 | 0 | 35 | 0%
Time Slots | 13 | 0 | 0 | 0 | 13 | 0%
Doctor - Requests | 17 | 0 | 0 | 0 | 17 | 0%
Admin - Bookings | 21 | 0 | 0 | 0 | 21 | 0%
Admin - Dashboard | 10 | 0 | 0 | 0 | 10 | 0%
Admin - Doctors, Technicians, Settings | 9 | 0 | 0 | 0 | 9 | 0%
End-to-End | 10 | 0 | 0 | 0 | 10 | 0%
UI Quality | 9 | 0 | 0 | 0 | 9 | 0%
Security & Rules | 16 | 0 | 0 | 0 | 16 | 0%
Performance & Scale | 8 | 0 | 0 | 0 | 8 | 0%
Device & Compatibility | 6 | 0 | 0 | 0 | 6 | 0%
Release & Deployment | 12 | 0 | 0 | 0 | 12 | 0%
TOTAL | 217 | 0 | 0 | 0 | 217 | 0%
Smoke cases (run after every change) | 77
P0 cases not yet passed | 92
Release gate: all P0 = Pass, all Smoke + Regression = Pass, no open Critical/High issue.
Priority: P0 blocker, P1 important, P2 nice-to-have. Suite: Smoke = quick check after every change, Regression = full run before release.
Fill 'Actual Result' and 'Status' (dropdown) while testing. Statuses: Not Run, Pass, Fail, Blocked.

## Test Cases
ID | Module | Type | Priority | Suite | Test Case | Steps | Expected Result | Actual Result | Notes | Bug / Ref | Status
AUTH-01 | Auth - Doctor | Positive | P0 | Smoke | Google sign-up (new doctor) lands on Home | 1. Fresh install 2. Tap Continue with Google 3. Pick a new Google account | Account created; goes straight to Home (no profile-setup screen); name from Google shown |  |  |  | Not Run
AUTH-02 | Auth - Doctor | Positive | P0 | Smoke | Google sign-in (returning doctor) opens same account | 1. Sign out 2. Continue with Google using same account | Same uid, same requests and profile as before |  |  |  | Not Run
AUTH-03 | Auth - Doctor | Negative | P2 | Regression | Google picker cancelled | 1. Tap Continue with Google 2. Dismiss picker | Back on login, no error loop, button works again |  |  |  | Not Run
AUTH-04 | Auth - Doctor | Negative | P1 | Regression | Google sign-in with no internet | 1. Airplane mode 2. Tap Continue with Google | Friendly 'no internet' message; no crash |  |  |  | Not Run
AUTH-05 | Auth - Doctor | Positive | P0 | Smoke | Email registration goes straight to Home | 1. Register tab: name, clinic, email, password(6+) 2. Tap Register | Account created; opens Home directly |  |  |  | Not Run
AUTH-06 | Auth - Doctor | Negative | P1 | Regression | Register with empty name / clinic / email / password | Submit each field empty in turn | Inline 'is required' error for each; nothing created |  |  |  | Not Run
AUTH-07 | Auth - Doctor | Negative | P1 | Regression | Invalid email formats rejected | Try: abc, abc@, abc@com, @x.com, a b@c.com | 'Enter a valid email address' |  |  |  | Not Run
AUTH-08 | Auth - Doctor | Edge | P1 | Regression | Valid email with long ending accepted | Register with doctor@smilecare.dental, x@clinic.health, y@dr.clinic | All accepted (old rule allowed only 2-4 letters) |  |  |  | Not Run
AUTH-09 | Auth - Doctor | Negative | P1 | Regression | Password shorter than 6 rejected; exactly 6 accepted | Try 'abc12' then 'abc123' | 5 chars rejected with message; 6 chars accepted |  |  |  | Not Run
AUTH-10 | Auth - Doctor | Negative | P0 | Smoke | Register with an existing email | Register again with a used email | 'An account already exists... switch to Sign In' |  |  |  | Not Run
AUTH-11 | Auth - Doctor | Positive | P0 | Smoke | Email sign-in with valid credentials | Sign in with registered email + password | Opens Home with correct data |  |  |  | Not Run
AUTH-12 | Auth - Doctor | Negative | P0 | Smoke | Wrong password | Sign in with wrong password | 'Incorrect email or password' ; stays on login |  |  |  | Not Run
AUTH-13 | Auth - Doctor | Negative | P1 | Regression | Unknown email | Sign in with unregistered email | Friendly error, no crash |  |  |  | Not Run
AUTH-14 | Auth - Doctor | Positive | P1 | Regression | Forgot password | 1. Enter email 2. Tap Forgot password | Reset link sent message; link works; old password stops working |  |  |  | Not Run
AUTH-15 | Auth - Doctor | Negative | P2 | Regression | Forgot password with empty email | Tap Forgot password with email blank | Asks for email first |  |  |  | Not Run
AUTH-16 | Auth - Doctor | Edge | P2 | Regression | Email with spaces / capital letters | Sign in with ' Doctor@Clinic.COM ' | Trimmed; login works |  |  |  | Not Run
AUTH-17 | Auth - Doctor | Positive | P0 | Smoke | Session persists after app kill and phone reboot | 1. Sign in 2. Force-close app 3. Reboot phone 4. Open app | Opens directly on Home with the SAME account; no login screen |  |  |  | Not Run
AUTH-18 | Auth - Doctor | Positive | P1 | Regression | Same account after reinstall | 1. Uninstall and reinstall 2. Sign in with same Google/email | Same data (requests, profile) restored |  |  |  | Not Run
AUTH-19 | Auth - Doctor | Positive | P0 | Smoke | Sign out clears state | 1. Sign out 2. Press Back 3. Sign in with another account | Back does not reopen app; second account sees none of the first account's data |  |  |  | Not Run
AUTH-20 | Auth - Doctor | Negative | P2 | Regression | Disabled account | Disable user in Firebase console, then sign in | 'Account disabled, contact support' |  |  |  | Not Run
AUTH-21 | Auth - Doctor | Negative | P2 | Regression | Too many failed attempts | Wrong password 8-10 times | 'Too many attempts' message; app responsive |  |  |  | Not Run
AUTH-22 | Auth - Doctor | Positive | P0 | Smoke | Phone OTP removed | Open login screen and all auth screens | No phone/OTP tab, no 'Fill test phone/OTP' buttons, no /otp route |  |  |  | Not Run
AUTH-23 | Auth - Doctor | Security | P0 | Smoke | No admin link or test logins on doctor login | Inspect login screen | No 'Admin Portal' link, no 1-Click Admin/Doctor buttons, no prefilled credentials |  |  |  | Not Run
AUTH-24 | Auth - Doctor | Positive | P1 | Regression | Login and register screens have no overflow | Open at 320x568 and 360x640; open keyboard; font scale 1.3 | No yellow-black stripes; form scrolls; buttons reachable |  |  |  | Not Run
ADA-01 | Auth - Admin | Positive | P0 | Smoke | Admin signs in with Google admin email | Sign in with the admin Gmail (has admin claim) | Lands on Admin Dashboard |  |  |  | Not Run
ADA-02 | Auth - Admin | Positive | P1 | Regression | Admin email/password (verified email) | Sign in with admin email+password | Lands on Admin Dashboard |  |  |  | Not Run
ADA-03 | Auth - Admin | Security | P0 | Smoke | Non-admin never reaches admin | Sign in as a doctor; try opening /admin and sub-routes | Redirected to doctor Home; no admin data |  |  |  | Not Run
ADA-04 | Auth - Admin | Security | P0 | Regression | Unverified-email admin is blocked | Admin email/password account with email not verified | Cannot read admin data / not routed to admin |  |  |  | Not Run
ADA-05 | Auth - Admin | Positive | P1 | Regression | Keep me signed in | Sign in as admin; kill app; reopen | Still signed in on Admin |  |  |  | Not Run
ADA-06 | Auth - Admin | Positive | P1 | Regression | Change password sends link to Gmail | As email/password admin: Change password | Reset email received; new password works; old fails |  |  |  | Not Run
ADA-07 | Auth - Admin | Positive | P2 | Regression | Google admin has no password option | Open admin settings as Google admin | Shows 'Managed by Google' |  |  |  | Not Run
ADA-08 | Auth - Admin | Security | P0 | Regression | Removing admin claim removes access | Remove claim; re-login or wait for token refresh | Access to admin lost; routed as doctor |  |  |  | Not Run
ADA-09 | Auth - Admin | Security | P0 | Smoke | Admin cannot open doctor booking routes | Signed in as admin; open /dentist/book | Redirected to /admin |  |  |  | Not Run
ADA-10 | Auth - Admin | Positive | P1 | Regression | Admin sign out | Tap Sign out; press Back | Returns to login; Back does not reopen admin |  |  |  | Not Run
ADA-11 | Auth - Admin | Security | P0 | Smoke | No client-side admin creation / hardcoded admin creds | Review code and release APK strings | No admin password or demo password in app; no admin sign-up code |  |  |  | Not Run
PRF-01 | Profile | Positive | P1 | Regression | Profile screen shows details | Open Profile | Name, clinic, mobile, support phone, Privacy Policy, Terms, Sign out, Delete account visible |  |  |  | Not Run
PRF-02 | Profile | Positive | P0 | Smoke | First booking saves clinic, mobile, address to profile | Complete first booking; start a second | Second booking form prefilled with saved clinic, mobile, address |  |  |  | Not Run
PRF-03 | Profile | Positive | P2 | Regression | Edit profile | Change clinic name and mobile; save | Saved; used in next booking |  |  |  | Not Run
PRF-04 | Profile | Negative | P2 | Regression | Profile mobile validation | Enter invalid mobile in profile | Rejected with message |  |  |  | Not Run
PRF-05 | Profile | Positive | P1 | Regression | Delete my account | Delete account and confirm | Account and personal data removed or anonymised; signed out; cannot sign in with old data |  |  |  | Not Run
PRF-06 | Profile | Positive | P1 | Regression | Privacy Policy and Terms links open | Tap each link | Pages open in browser; URLs are live |  |  |  | Not Run
HOME-01 | Doctor - Home | Positive | P0 | Smoke | Status summary tiles show correct live counts | Have 1 request in each of Pending, Assigned, In progress, Completed; open Home | Tiles show 1 each |  |  |  | Not Run
HOME-02 | Doctor - Home | Positive | P0 | Smoke | Each tile opens My Requests with that filter | Tap each tile | List opens already filtered to that status and shows the right requests |  |  |  | Not Run
HOME-03 | Doctor - Home | Positive | P0 | Smoke | Active requests shows ALL active, not just one | Have 3 active requests | All 3 listed (max 5, then 'View all') |  |  |  | Not Run
HOME-04 | Doctor - Home | Positive | P0 | Smoke | My Service History opens full list | Tap My Service History | Opens My Requests with filter All; the history is different from the active list |  |  |  | Not Run
HOME-05 | Doctor - Home | Positive | P0 | Smoke | Category tile preselects category | Tap each category tile (Dental Chair ... Suction) | Booking form opens with that category preselected; no error screen |  |  |  | Not Run
HOME-06 | Doctor - Home | Positive | P1 | Regression | Live update when admin changes status | Keep Home open; admin assigns technician | Counts and cards update without refresh |  |  |  | Not Run
HOME-07 | Doctor - Home | Positive | P1 | Regression | Empty state for new doctor | Open Home with no requests | Friendly empty state; tiles show 0 |  |  |  | Not Run
HOME-08 | Doctor - Home | Positive | P1 | Regression | Cancelled requests are reachable | Cancel a request; use Home / history | Cancelled filter in My Requests shows it |  |  |  | Not Run
HOME-09 | Doctor - Home | Positive | P1 | Regression | No overflow on Home | Check at small sizes, font scale, dark mode | No yellow-black stripes |  |  |  | Not Run
HOME-10 | Doctor - Home | Positive | P2 | Regression | Support phone visible | Open Home / Profile | Support number shown; tapping opens dialer |  |  |  | Not Run
BKG-01 | Doctor - Booking | Positive | P0 | Smoke | Category dropdown works for every category | Open booking; select each category one by one | Each is selectable; no 'exactly one item with value' assertion; no red error screen |  |  |  | Not Run
BKG-02 | Doctor - Booking | Edge | P0 | Regression | Duplicate category in config does not crash | Put the same category twice in Firestore config; open booking | Shown once; no crash |  |  |  | Not Run
BKG-03 | Doctor - Booking | Edge | P1 | Regression | Category removed while form is open | Select a category; admin deactivates it; keep editing | Selection cleared with a message; no crash |  |  |  | Not Run
BKG-04 | Doctor - Booking | Edge | P1 | Regression | Empty category config | Set issueTypes to empty list | Friendly message; no crash |  |  |  | Not Run
BKG-05 | Doctor - Booking | Positive | P0 | Smoke | Description accepts any words | Enter 'AC leak', then 'x' | Accepted (no 10-character minimum) |  |  |  | Not Run
BKG-06 | Doctor - Booking | Negative | P1 | Regression | Empty or spaces-only description rejected | Leave empty; enter 15 spaces | 'Description is required' |  |  |  | Not Run
BKG-07 | Doctor - Booking | Edge | P2 | Regression | Maximum 500 characters | Paste 600 characters | Limited to 500 or clear error |  |  |  | Not Run
BKG-08 | Doctor - Booking | Edge | P2 | Regression | Unicode and emoji description | Enter Telugu/Hindi text, emoji, symbols | Saved and shown correctly on doctor and admin screens |  |  |  | Not Run
BKG-09 | Doctor - Booking | Positive | P0 | Smoke | No image or video option anywhere | Inspect booking, review, detail, admin screens; check manifest and Storage rules | No photo/video UI; no camera/photo permission; Storage rules deny all |  |  |  | Not Run
BKG-10 | Doctor - Booking | Positive | P1 | Regression | Doctor and clinic name prefilled and editable | Open contact step | Prefilled from profile; can be edited |  |  |  | Not Run
BKG-11 | Doctor - Booking | Negative | P0 | Smoke | Mobile number is mandatory | Leave mobile empty; continue | 'Phone number is required'; cannot continue |  |  |  | Not Run
BKG-12 | Doctor - Booking | Negative | P1 | Regression | Invalid mobile numbers rejected | Try 9 digits, 11 digits, starts with 5, letters | 'Enter a valid 10-digit phone number' |  |  |  | Not Run
BKG-13 | Doctor - Booking | Edge | P2 | Regression | Mobile with +91 and spaces | Enter '+91 98765 43210' | Accepted and normalised |  |  |  | Not Run
BKG-14 | Doctor - Booking | Negative | P0 | Smoke | Address line required | Leave address empty | 'Address is required' |  |  |  | Not Run
BKG-15 | Doctor - Booking | Positive | P2 | Regression | Landmark and area optional | Leave blank | Booking proceeds |  |  |  | Not Run
BKG-16 | Doctor - Booking | Negative | P0 | Smoke | Pincode required, 6 digits | Empty / 5 digits / letters | Rejected with message |  |  |  | Not Run
BKG-17 | Doctor - Booking | Negative | P0 | Smoke | Non-Hyderabad pincode blocked | Enter 560001 (Bengaluru) | 'We currently serve Hyderabad only'; cannot continue |  |  |  | Not Run
BKG-18 | Doctor - Booking | Positive | P1 | Regression | Hyderabad pincodes accepted | Enter 500034, 500081, 501301, 502032 | Accepted (per configured prefixes) |  |  |  | Not Run
BKG-19 | Doctor - Booking | Positive | P2 | Regression | City locked to Hyderabad | Try to edit city | Read-only 'Hyderabad' |  |  |  | Not Run
BKG-20 | Doctor - Booking | Positive | P0 | Smoke | Detect my location fills address | Tap Detect my location; allow permission (GPS on, inside Hyderabad) | Address, area, pincode filled; editable; lat/lng saved |  |  |  | Not Run
BKG-21 | Doctor - Booking | Negative | P1 | Regression | Location permission denied | Deny permission | Message; manual entry still works |  |  |  | Not Run
BKG-22 | Doctor - Booking | Negative | P1 | Regression | Location permanently denied | Deny with 'don't ask again'; tap button again | Offers to open app settings; manual entry works |  |  |  | Not Run
BKG-23 | Doctor - Booking | Negative | P1 | Regression | GPS switched off | Turn off location; tap button | Asks to enable location; no freeze |  |  |  | Not Run
BKG-24 | Doctor - Booking | Negative | P1 | Regression | Detected location outside Hyderabad | Use mock location in another city | 'We currently serve Hyderabad only' |  |  |  | Not Run
BKG-25 | Doctor - Booking | Negative | P2 | Regression | Geocoding fails (offline) | Go offline after GPS fix | Friendly message; manual entry possible |  |  |  | Not Run
BKG-26 | Doctor - Booking | Security | P1 | Regression | No paid Maps/Places API used | Review code, manifest, Google Cloud billing | No Maps SDK/Places key; location uses device geocoder only; no billing account needed for it |  |  |  | Not Run
BKG-27 | Doctor - Booking | Positive | P1 | Regression | Form keeps data on Back and forward | Fill steps; go back and forward | Entered data retained |  |  |  | Not Run
BKG-28 | Doctor - Booking | Positive | P0 | Smoke | Review shows all details correctly | Reach Review | Doctor, clinic, mobile, full address, category, description, slot, status text all correct |  |  |  | Not Run
BKG-29 | Doctor - Booking | Positive | P0 | Smoke | Review has no overflow and no fee lines | Open Review at small sizes | No stripes; no Rs 0 / visit fee / inspection charge; shows free-app and pay-technician text |  |  |  | Not Run
BKG-30 | Doctor - Booking | Positive | P0 | Smoke | Confirm creates request in NEW state | Tap Confirm Booking | Request saved with status NEW and all fields; success screen with short ID and call-you message |  |  |  | Not Run
BKG-31 | Doctor - Booking | Negative | P0 | Smoke | Double tap creates one request | Tap Confirm 3 times quickly | Exactly one request in doctor list and admin queue |  |  |  | Not Run
BKG-32 | Doctor - Booking | Negative | P1 | Regression | Submit while offline | Airplane mode; Confirm | Error message; no phantom request; retry works online |  |  |  | Not Run
BKG-33 | Doctor - Booking | Negative | P1 | Regression | Maximum open requests | Create 3 open requests; try a 4th | Clear message; booking blocked |  |  |  | Not Run
BKG-34 | Doctor - Booking | Positive | P2 | Regression | Back after success does not resubmit | Press Back on success screen | Goes Home; no duplicate |  |  |  | Not Run
BKG-35 | Doctor - Booking | Positive | P2 | Regression | Book again from cancelled request | Open cancelled request; tap Book again | Booking form prefilled; slot must be chosen again |  |  |  | Not Run
SLT-01 | Time Slots | Positive | P0 | Smoke | Dates are today to +7 days only | Open slot step | No past dates; last date is today+7 |  |  |  | Not Run
SLT-02 | Time Slots | Positive | P0 | Smoke | Three slots shown | Pick a future date | 9-12, 2-5, 6-9 slots shown |  |  |  | Not Run
SLT-03 | Time Slots | Positive | P0 | Smoke | Past slots disabled for today | Open at 3 PM | 9-12 and 2-5 disabled/hidden; 6-9 PM available |  |  |  | Not Run
SLT-04 | Time Slots | Edge | P0 | Smoke | Slot already started is not bookable | Open at 10:30 AM | 9-12 slot not selectable |  |  |  | Not Run
SLT-05 | Time Slots | Edge | P1 | Regression | 30-minute lead time | Open at 8:45 AM, then 8:15 AM | 8:45: 9-12 not bookable; 8:15: bookable (start >= now+30 min) |  |  |  | Not Run
SLT-06 | Time Slots | Edge | P1 | Regression | After 6 PM today has no slots | Open at 6:30 PM | Today shows no slots; next day available |  |  |  | Not Run
SLT-07 | Time Slots | Security | P0 | Regression | Wrong phone clock cannot book the past | Set phone date back; try booking yesterday's slot (or via API) | Rejected by Firestore rules (slotStart > server time) |  |  |  | Not Run
SLT-08 | Time Slots | Edge | P2 | Regression | Time zone | Set phone to another time zone | Slots still follow IST |  |  |  | Not Run
SLT-09 | Time Slots | Negative | P0 | Smoke | Slot is required | Skip slot; continue | 'Please choose a time slot' |  |  |  | Not Run
SLT-10 | Time Slots | Positive | P1 | Regression | Slot shown everywhere | Check Review, doctor detail, admin detail | Same date and slot shown on all |  |  |  | Not Run
SLT-11 | Time Slots | Edge | P1 | Regression | Slot expires while form is open | Open slot step 5 min before the lead cutoff; wait; Confirm | Re-validated; asks to choose a new slot |  |  |  | Not Run
SLT-12 | Time Slots | Edge | P2 | Regression | Midnight rollover | Keep form open past midnight | Date list refreshed; no past date |  |  |  | Not Run
SLT-13 | Time Slots | Positive | P1 | Regression | Admin changes slot config | Edit slot times in Settings | New slots appear for doctors without new release |  |  |  | Not Run
DR-01 | Doctor - Requests | Positive | P0 | Smoke | My Requests filter chips | Open My Requests | Chips: All, Pending, Assigned, In progress, Completed, Cancelled; each filters correctly |  |  |  | Not Run
DR-02 | Doctor - Requests | Positive | P0 | Smoke | Request detail shows technician and slot | Open an assigned request | Slot, technician name, tap-to-call phone, 'will call or visit during your slot', timeline |  |  |  | Not Run
DR-03 | Doctor - Requests | Positive | P0 | Smoke | Mark as completed asks for amount | Open assigned/in-progress request; tap Mark as completed | Dialog 'How much did you pay the technician?' |  |  |  | Not Run
DR-04 | Doctor - Requests | Negative | P0 | Smoke | Amount validation | Try empty, letters, negative, 12.5, 100001 | Rejected with message; only whole rupees 0-100000 accepted |  |  |  | Not Run
DR-05 | Doctor - Requests | Edge | P1 | Regression | Amount 0 allowed | Enter 0 | Accepted after confirmation (free visit) |  |  |  | Not Run
DR-06 | Doctor - Requests | Positive | P0 | Smoke | Confirmation step before closing | Enter 1500; continue | Shows 'Confirm you paid Rs 1500 and close ticket?'; Cancel returns without change |  |  |  | Not Run
DR-07 | Doctor - Requests | Positive | P0 | Smoke | Completed ticket saved and read-only | Confirm | Status COMPLETED; amountPaid, completedAt, completedBy=dentist saved; no further actions; admin sees it |  |  |  | Not Run
DR-08 | Doctor - Requests | Positive | P0 | Smoke | Doctor cancels NEW request with reason | Tap Cancel; pick reason | Status CANCELLED with reason and cancelledBy=dentist; admin sees reason |  |  |  | Not Run
DR-09 | Doctor - Requests | Negative | P1 | Regression | Reason mandatory; Other needs text | Try to cancel with no reason; choose Other with empty text | Blocked until reason (and text for Other) provided |  |  |  | Not Run
DR-10 | Doctor - Requests | Positive | P1 | Regression | Doctor cancels ASSIGNED request | Cancel after technician assigned | Allowed; admin sees it; technician no longer expected |  |  |  | Not Run
DR-11 | Doctor - Requests | Negative | P0 | Regression | No cancel after IN_PROGRESS | Open IN_PROGRESS request | No Cancel button; text to contact support |  |  |  | Not Run
DR-12 | Doctor - Requests | Positive | P1 | Regression | Admin denies service; doctor sees reason | Admin cancels with 'Outside service area' | Doctor sees Cancelled + reason + Book again |  |  |  | Not Run
DR-13 | Doctor - Requests | Positive | P1 | Regression | Technician denies: admin cancels or reassigns | Admin cancels with 'Technician unable to attend'; or reassigns | Doctor sees update either way; no stale technician shown |  |  |  | Not Run
DR-14 | Doctor - Requests | Positive | P1 | Regression | Doctor never closes: admin closes on behalf | Admin closes with amount | Doctor sees Completed; marked 'closed by admin' |  |  |  | Not Run
DR-15 | Doctor - Requests | Positive | P1 | Regression | Real-time updates on detail screen | Admin changes status while doctor has detail open | Updates within seconds without refresh |  |  |  | Not Run
DR-16 | Doctor - Requests | Edge | P1 | Regression | Pagination with 25+ requests | Create 25+ requests | 20 load first, more on scroll; none missing |  |  |  | Not Run
DR-17 | Doctor - Requests | Security | P1 | Regression | Internal admin notes invisible to doctor | Admin saves a note | Doctor cannot see it in app or via query |  |  |  | Not Run
ADM-01 | Admin - Bookings | Positive | P0 | Smoke | Filter chips with counts | Open Bookings | Pending dispatch, Technician assigned, In progress, Completed, Cancelled, All; counts correct |  |  |  | Not Run
ADM-02 | Admin - Bookings | Positive | P1 | Regression | Sorting and pagination | Have 50 requests | Sorted by slot time; 20 per page; no duplicates |  |  |  | Not Run
ADM-03 | Admin - Bookings | Positive | P1 | Regression | Search | Search clinic, doctor, mobile, short ID | Correct matches; empty result message |  |  |  | Not Run
ADM-04 | Admin - Bookings | Positive | P0 | Smoke | Ticket detail shows full info | Open a new ticket | Clinic, doctor, mobile (tap-to-call), address, landmark, pincode, category, description, slot, timeline |  |  |  | Not Run
ADM-05 | Admin - Bookings | Positive | P1 | Regression | Open in Google Maps | Tap Open in Google Maps | Maps opens at the clinic location/address |  |  |  | Not Run
ADM-06 | Admin - Bookings | Positive | P0 | Smoke | Assign technician (active only) | Tap Assign; choose technician | Status ASSIGNED; doctor sees technician name/phone and slot message |  |  |  | Not Run
ADM-07 | Admin - Bookings | Positive | P1 | Regression | Reassign before in-progress | Reassign to another technician | Doctor sees new technician; event logged |  |  |  | Not Run
ADM-08 | Admin - Bookings | Negative | P0 | Smoke | Set In Progress disabled until assigned | Open NEW ticket | Set In Progress disabled/hidden |  |  |  | Not Run
ADM-09 | Admin - Bookings | Positive | P0 | Smoke | Set In Progress after assignment | Open ASSIGNED ticket; tap Set In Progress | Status IN_PROGRESS; doctor sees it live |  |  |  | Not Run
ADM-10 | Admin - Bookings | Positive | P0 | Smoke | Close on behalf asks amount | Open ASSIGNED/IN_PROGRESS; tap Close on behalf | Amount dialog + confirm; completedBy=admin |  |  |  | Not Run
ADM-11 | Admin - Bookings | Negative | P1 | Regression | Amount validation (admin) | Same invalid amounts as doctor | Rejected |  |  |  | Not Run
ADM-12 | Admin - Bookings | Positive | P0 | Smoke | Cancel/deny needs reason | Cancel ticket with each admin reason | Saved with cancelledBy=admin and reason; doctor sees it |  |  |  | Not Run
ADM-13 | Admin - Bookings | Negative | P1 | Regression | Reason mandatory; Other needs text | Try empty reason | Blocked |  |  |  | Not Run
ADM-14 | Admin - Bookings | Positive | P0 | Smoke | Doctor closes -> admin sees Completed + amount | Doctor completes with amount | Admin ticket shows Completed, amount, 'closed by doctor' |  |  |  | Not Run
ADM-15 | Admin - Bookings | Negative | P0 | Regression | Final states have no actions | Open COMPLETED and CANCELLED tickets | No status buttons |  |  |  | Not Run
ADM-16 | Admin - Bookings | Security | P0 | Regression | Invalid transition rejected by server | Via API try NEW->COMPLETED, NEW->IN_PROGRESS, COMPLETED->NEW | All denied by rules |  |  |  | Not Run
ADM-17 | Admin - Bookings | Edge | P0 | Regression | Concurrent actions | Admin cancels while doctor closes at the same moment | One wins; other gets 'already updated'; data consistent |  |  |  | Not Run
ADM-18 | Admin - Bookings | Edge | P1 | Regression | Two admins assign at once | Assign two different technicians simultaneously | Last valid state consistent; no corruption |  |  |  | Not Run
ADM-19 | Admin - Bookings | Positive | P1 | Regression | Internal notes saved | Add and save note | Persists; hidden from doctor |  |  |  | Not Run
ADM-20 | Admin - Bookings | Positive | P1 | Regression | Audit trail | Perform assign, start, complete | Events recorded with who and when |  |  |  | Not Run
ADM-21 | Admin - Bookings | Negative | P2 | Regression | No technicians available | Deactivate all technicians; try assign | 'No technicians available' with link to add one |  |  |  | Not Run
DSH-01 | Admin - Dashboard | Positive | P0 | Smoke | KPIs match data | Seed a known dataset; open Dashboard | Pending, assigned, in progress, completed, cancelled, doctors, technicians counts all match |  |  |  | Not Run
DSH-02 | Admin - Dashboard | Positive | P0 | Smoke | Every tile is tappable and filtered | Tap each tile | Opens the matching filtered list; counts agree |  |  |  | Not Run
DSH-03 | Admin - Dashboard | Positive | P1 | Regression | Today / 7 days / 30 days filter | Switch range | Numbers change correctly |  |  |  | Not Run
DSH-04 | Admin - Dashboard | Positive | P0 | Smoke | 'Paid to technicians' sum is correct | Complete tickets with 1000, 1500, 0 | Sum = 2500; excludes cancelled and open tickets |  |  |  | Not Run
DSH-05 | Admin - Dashboard | Positive | P1 | Regression | Needs attention list | Create: pending >2h, today slot unassigned, slot passed still ASSIGNED, active >48h | Each appears with reason; tapping opens the ticket |  |  |  | Not Run
DSH-06 | Admin - Dashboard | Positive | P2 | Regression | Empty state | New project with no data | Zeros and helpful text; no crash |  |  |  | Not Run
DSH-07 | Admin - Dashboard | Positive | P1 | Regression | No non-actionable or unclear labels | Review all dashboard text | No 'Active Leads' / 'Total Doc Revenue'; names clear |  |  |  | Not Run
DSH-08 | Admin - Dashboard | Non-functional | P0 | Regression | Scales with large data | Seed 10,000+ requests in staging | Uses count/sum aggregation; opens in < 3 s; reads stay small |  |  |  | Not Run
DSH-09 | Admin - Dashboard | Positive | P2 | Regression | Pull to refresh | Pull down | Numbers refresh |  |  |  | Not Run
DSH-10 | Admin - Dashboard | Positive | P1 | Regression | No overflow on dashboard | Small sizes and font scale | No yellow-black stripes |  |  |  | Not Run
ADT-01 | Admin - Doctors, Technicians, Settings | Positive | P1 | Regression | Doctors list and search | Open Doctors; search by name, phone, clinic | Paginated; matches shown |  |  |  | Not Run
ADT-02 | Admin - Doctors, Technicians, Settings | Positive | P1 | Regression | Doctor profile | Tap a doctor | Call button; doctor's requests listed |  |  |  | Not Run
ADT-03 | Admin - Doctors, Technicians, Settings | Positive | P0 | Smoke | Add technician | Technicians > Add; name, phone, area | Saved; appears in assign list |  |  |  | Not Run
ADT-04 | Admin - Doctors, Technicians, Settings | Negative | P1 | Regression | Technician validation | Empty name; invalid phone; duplicate phone | Rejected with message |  |  |  | Not Run
ADT-05 | Admin - Doctors, Technicians, Settings | Positive | P1 | Regression | Edit and deactivate technician | Edit; deactivate | Inactive technician not in assign list; old tickets keep name |  |  |  | Not Run
ADT-06 | Admin - Doctors, Technicians, Settings | Security | P1 | Regression | No seed button or placeholder technicians | Inspect Technicians screen and data | Seed button gone; no fake numbers |  |  |  | Not Run
ADT-07 | Admin - Doctors, Technicians, Settings | Positive | P0 | Smoke | Add/rename/deactivate category | Settings > Categories | Doctor dropdown updates; no hard delete; old tickets still show label |  |  |  | Not Run
ADT-08 | Admin - Doctors, Technicians, Settings | Positive | P1 | Regression | Slots, days ahead, pincodes, reasons, support phone, max open requests editable | Change each in Settings | Doctor app reflects change without new release |  |  |  | Not Run
ADT-09 | Admin - Doctors, Technicians, Settings | Negative | P2 | Regression | Settings validation | Empty category; duplicate; invalid pincode prefix | Rejected |  |  |  | Not Run
E2E-01 | End-to-End | E2E | P0 | Smoke | Happy path (Google) | 1. Doctor: Google sign-up -> Home 2. Book: category, description, mobile, address, slot 3. Review -> Confirm 4. Admin: open ticket, assign technician 5. Doctor sees technician 6. Admin: Set In Progress 7. Doctor: Mark completed, amount 1500, confirm 8. Admin: ticket Completed; dashboard Paid to technicians +1500 | Every step works; both sides update live; numbers correct |  |  |  | Not Run
E2E-02 | End-to-End | E2E | P0 | Smoke | Happy path (email registration) | Same as E2E-01 but register with email | Register lands on Home; rest same |  |  |  | Not Run
E2E-03 | End-to-End | E2E | P1 | Regression | Doctor cancels | Book; doctor cancels with reason | Admin sees Cancelled + reason; dashboard cancelled +1 |  |  |  | Not Run
E2E-04 | End-to-End | E2E | P1 | Regression | Admin denies service (outside area) | Book with Hyderabad pincode but admin denies 'Equipment not supported' | Doctor sees reason; Book again works |  |  |  | Not Run
E2E-05 | End-to-End | E2E | P1 | Regression | Admin closes on behalf | Technician done; doctor does not close; admin closes with amount | Completed, closed by admin |  |  |  | Not Run
E2E-06 | End-to-End | E2E | P1 | Regression | Technician no-show -> reassign | Assign; slot passes; admin reassigns | Needs attention flags it; reassign works |  |  |  | Not Run
E2E-07 | End-to-End | E2E | P1 | Regression | Slot passes unassigned | Book; do not assign past slot | Appears in Needs attention; admin can cancel with reason |  |  |  | Not Run
E2E-08 | End-to-End | E2E | P1 | Regression | Several doctors, one admin | 3 doctors book; admin handles all | Each doctor sees only own tickets; admin sees all |  |  |  | Not Run
E2E-09 | End-to-End | E2E | P1 | Regression | Offline then online | Book offline (fails), retry online | One request only |  |  |  | Not Run
E2E-10 | End-to-End | E2E | P1 | Regression | Kill app mid-flow and reopen | Kill during booking and during closing | No duplicate or half-saved data; same account |  |  |  | Not Run
UI-01 | UI Quality | Positive | P0 | Smoke | No overflow on ANY screen | Open every screen (login, register, home, booking steps, review, success, requests, detail, profile, admin screens) at 320x568, 360x640, 412x915 | No yellow-black stripes or 'RenderFlex overflowed' in logs |  |  |  | Not Run
UI-02 | UI Quality | Positive | P1 | Regression | Keyboard open | Focus every text field | Field visible; form scrolls; buttons reachable |  |  |  | Not Run
UI-03 | UI Quality | Positive | P1 | Regression | Font scale 1.3 and 2.0 | Change system font size | No overflow; text readable |  |  |  | Not Run
UI-04 | UI Quality | Positive | P2 | Regression | Dark mode and landscape | Switch | Readable; no overflow |  |  |  | Not Run
UI-05 | UI Quality | Positive | P1 | Regression | Loading, empty and error states exist | Slow network, empty data, forced error | Every screen shows a proper state; no infinite spinner |  |  |  | Not Run
UI-06 | UI Quality | Positive | P1 | Regression | No debug UI in release | Install release build | No BETA/STAGING ribbon, no debug banner, no test text |  |  |  | Not Run
UI-07 | UI Quality | Positive | P2 | Regression | Back button behaviour | Back on every screen | Predictable; no dead ends |  |  |  | Not Run
UI-08 | UI Quality | Positive | P2 | Regression | Tap targets and contrast | Check buttons >= 48dp and readable colours | Meets basic accessibility |  |  |  | Not Run
UI-09 | UI Quality | Positive | P1 | Regression | Copy review | Read all texts | No 'Rs 0 fee / free diagnosis' claims; clear that technician is paid directly |  |  |  | Not Run
SEC-01 | Security & Rules | Security | P0 | Smoke | No credentials or test buttons in release APK | Extract strings from release APK | No passwords, admin/demo emails, test OTP, 1-click login code |  |  |  | Not Run
SEC-02 | Security & Rules | Security | P0 | Smoke | Old admin/demo credentials rotated and accounts removed | Try signing in with old admin and demo passwords | Fail |  |  |  | Not Run
SEC-03 | Security & Rules | Security | P0 | Smoke | Doctor cannot make self admin | Try writing role/admin fields on own user doc | Denied |  |  |  | Not Run
SEC-04 | Security & Rules | Security | P0 | Smoke | Doctor cannot read other doctors' requests/profiles | Query as Doctor A for Doctor B | Permission denied |  |  |  | Not Run
SEC-05 | Security & Rules | Security | P0 | Smoke | Doctor cannot assign or set status like admin | Try updating assignedTechnician or status to IN_PROGRESS | Denied |  |  |  | Not Run
SEC-06 | Security & Rules | Security | P0 | Smoke | Unauthenticated access blocked | Read/write all collections with no login | All denied |  |  |  | Not Run
SEC-07 | Security & Rules | Security | P0 | Regression | Technicians and settings write protection | Doctor tries to edit technicians/config; read technicians list | Denied (technicians admin-only; config read-only) |  |  |  | Not Run
SEC-08 | Security & Rules | Security | P0 | Regression | Doctor create rules | Create with another dentistId, status ASSIGNED, past slot, amountPaid, 600-char text, bad mobile | All denied |  |  |  | Not Run
SEC-09 | Security & Rules | Security | P0 | Regression | Doctor update rules | Edit description/slot/clinic after creation; set amount outside completion | Denied except allowed transitions |  |  |  | Not Run
SEC-10 | Security & Rules | Security | P0 | Regression | Storage rules deny all | Try upload/read | Denied |  |  |  | Not Run
SEC-11 | Security & Rules | Security | P0 | Smoke | App Check enforced | Call Firestore/Auth from a non-app client | Rejected |  |  |  | Not Run
SEC-12 | Security & Rules | Security | P0 | Smoke | Release build signed and not debuggable | Check signing and debuggable flag | Release key; not debuggable |  |  |  | Not Run
SEC-13 | Security & Rules | Security | P1 | Regression | No secrets in repo | Scan repo and history for keystore, service account, passwords | None found |  |  |  | Not Run
SEC-14 | Security & Rules | Security | P0 | Smoke | Rules unit tests pass | Run emulator rules test suite | All pass |  |  |  | Not Run
SEC-15 | Security & Rules | Security | P1 | Regression | Personal data privacy | Doctor views own data only; admin notes hidden | No leakage |  |  |  | Not Run
SEC-16 | Security & Rules | Security | P2 | Regression | Input injection | Enter HTML/script/very long strings in all fields | Stored/displayed as plain text; no crash |  |  |  | Not Run
PERF-01 | Performance & Scale | Non-functional | P1 | Regression | Cold start | Release build, mid-range phone | < 3-4 s to first screen |  |  |  | Not Run
PERF-02 | Performance & Scale | Non-functional | P0 | Regression | Pagination everywhere | Open any list with 5,000 records | 20 per page; memory stable |  |  |  | Not Run
PERF-03 | Performance & Scale | Non-functional | P0 | Regression | No missing-index errors | Use every filter/sort combination on staging and prod | No 'query requires an index' errors; indexes deployed from firestore.indexes.json |  |  |  | Not Run
PERF-04 | Performance & Scale | Non-functional | P1 | Regression | Firestore read budget | Count reads for a typical session | Home <= ~10 reads; no whole-collection streams |  |  |  | Not Run
PERF-05 | Performance & Scale | Non-functional | P1 | Regression | Listeners disposed | Navigate in/out of screens repeatedly | No growing reads or memory; no leaks |  |  |  | Not Run
PERF-06 | Performance & Scale | Non-functional | P1 | Regression | Simulated load | Seed 1,000 doctors / 5,000 requests; run scripted bookings and status changes | No errors; latency acceptable |  |  |  | Not Run
PERF-07 | Performance & Scale | Non-functional | P2 | Regression | App size | Release AAB size | Reasonable (target < 40 MB download) |  |  |  | Not Run
PERF-08 | Performance & Scale | Non-functional | P1 | Regression | Budget alerts and quotas | Check billing alerts and Firestore quotas | Alerts set; Blaze plan active |  |  |  | Not Run
DEV-01 | Device & Compatibility | Non-functional | P1 | Regression | Android versions | Android 8, 10, 12, 14, 15 | Installs and runs core flow |  |  |  | Not Run
DEV-02 | Device & Compatibility | Non-functional | P1 | Regression | Screen sizes | Small phone, large phone, tablet | No overflow |  |  |  | Not Run
DEV-03 | Device & Compatibility | Non-functional | P1 | Regression | Slow network | Throttle to 2G/3G | Loaders and clear errors; no hangs |  |  |  | Not Run
DEV-04 | Device & Compatibility | Non-functional | P2 | Regression | Rotation and app switching | Rotate; background 5 min | State preserved; still signed in |  |  |  | Not Run
DEV-05 | Device & Compatibility | Non-functional | P1 | Regression | Calls and Maps links | Tap-to-call and Open in Maps on real phone | Dialer/Maps open correctly |  |  |  | Not Run
DEV-06 | Device & Compatibility | Non-functional | P1 | Regression | Upgrade install | Install new build over old | Stays signed in; data intact |  |  |  | Not Run
DEP-01 | Release & Deployment | Positive | P0 | Smoke | Separate dev/staging/prod projects and flavors | Check build flavors | Prod flavor uses prod project only; no ribbon |  |  |  | Not Run
DEP-02 | Release & Deployment | Positive | P0 | Smoke | Staging full regression passed | Run all cases on staging release build | All Smoke + Regression pass |  |  |  | Not Run
DEP-03 | Release & Deployment | Positive | P0 | Smoke | Prod project configured | Check Blaze, Auth providers, authorized domains, SHA-1/SHA-256 (release + Play App Signing), App Check, Crashlytics, PITR | All set |  |  |  | Not Run
DEP-04 | Release & Deployment | Positive | P0 | Smoke | Rules and indexes deployed to prod | firebase deploy --only firestore:rules,firestore:indexes | Success; rules tests passed before deploy |  |  |  | Not Run
DEP-05 | Release & Deployment | Positive | P0 | Smoke | Admin claim only for admin Gmail | Run script; test with doctor account | Only admin email reaches admin |  |  |  | Not Run
DEP-06 | Release & Deployment | Positive | P0 | Smoke | Prod config seeded, no test data | Check bookingConfig, technicians, users, requests | Real categories, slots, pincodes, reasons, support phone, real technicians; no demo accounts or fake requests |  |  |  | Not Run
DEP-07 | Release & Deployment | Positive | P0 | Smoke | Prod smoke test on real phone | Run E2E-01 with a fresh Google account; delete test data | Passes; data cleaned |  |  |  | Not Run
DEP-08 | Release & Deployment | Positive | P1 | Regression | Crashlytics and Analytics receive data | Trigger a test event/non-fatal | Visible in console |  |  |  | Not Run
DEP-09 | Release & Deployment | Positive | P0 | Smoke | Play Console readiness | Privacy policy URL, data safety form, account deletion info, app signing, internal test track | Complete |  |  |  | Not Run
DEP-10 | Release & Deployment | Positive | P1 | Regression | Rollback plan | Confirm previous AAB and Remote Config min version | Documented and tested |  |  |  | Not Run
DEP-11 | Release & Deployment | Positive | P1 | Regression | Staged rollout | Release to small percentage first | Monitor crashes and Firestore usage before 100% |  |  |  | Not Run
DEP-12 | Release & Deployment | Positive | P1 | Regression | Backups | Check PITR/export schedule | Enabled |  |  |  | Not Run

## Issues & Changes
# | Severity | Reported / found | Cause found in the APK | Required change | Test IDs
I1 | Critical | Hard-coded admin and demo credentials; 1-Click Admin / Doctor login; Fill Test OTP; client-side admin account creation | Constants and login-screen code inside the app (unchanged in both APKs) | Remove all of it; rotate passwords; admin by Firebase custom claim set by a script | AUTH-23, ADA-11, SEC-01, SEC-02, SEC-03
I2 | Critical | Production rules not verified; role is stored in a user document | APK cannot show the rules | Deny-by-default Firestore/Storage rules; rules unit tests; enforce status transitions server-side | SEC-03 to SEC-10, SEC-14, ADM-16
I3 | High | Home dropdown tabs (Dental Chair ... Suction Pipe) show red error 'exactly one item with DropdownButton value' | Dropdown built from config list with initialValue; tile names differ from config names; list can have duplicates/empty/changes; tiles open booking without category | One category list with codes; de-duplicate; reset invalid selection; tiles preselect by code | BKG-01 to BKG-04, HOME-05
I4 | High | Active lead card does not show all requests; History opens same screen | Home shows only active.first; app-bar icon and History both push the list with filter All | Status tiles + all active requests; deep link to filtered list | HOME-01 to HOME-04, DR-01
I5 | High | Yellow-black overflow stripes (26 px etc.) on register, home, review, admin dashboard | Fixed layouts without scroll or flexible widgets | Make all screens scrollable/flexible; add overflow test at 3 sizes | UI-01 to UI-04, AUTH-24, HOME-09, BKG-29, DSH-10
I6 | High | 'Use GPS' cannot work on Android | Manifest has no ACCESS_FINE/COARSE_LOCATION | Add permissions; use free device geocoder to fill address; no paid Maps/Places API | BKG-20 to BKG-26
I7 | High | Description must be 10+ characters | Validators.description | Any words, 1-500 chars | BKG-05 to BKG-08
I8 | High | Images/videos cost storage | Photo/video config, models, Storage code | Remove everything; Storage rules deny all | BKG-09, SEC-10
I9 | High | Address: Hyderabad only; landmark, pincode; mobile mandatory; auto-fill by location | Address is a single free-text; no pincode or mobile check | Structured address, pincode prefix check, mandatory mobile, Detect my location | BKG-11 to BKG-26
I10 | High | Login: remove OTP and Admin Portal; Google preferred; direct to Home after register; same account every time | Phone OTP tab, admin link, profile-setup gate | One login screen, Google first, no profile gate, persistent session | AUTH-01 to AUTH-24
I11 | High | Admin sign-in by admin email only; remember me; change password | Separate admin login with fixed credentials | Same login; admin claim routes to /admin; change password via Gmail link | ADA-01 to ADA-10
I12 | Medium | Valid emails like .dental rejected | Regex allows 2-4 letter endings only | Looser email rule | AUTH-08
I13 | High | Admin dashboard tiles not actionable; unclear numbers; revenue meaning unclear | Static tiles; whole collections streamed | Tappable KPIs, Needs attention, aggregation queries, 'Paid to technicians' label | DSH-01 to DSH-10
I14 | High | Status buttons not linked; In Progress should need assignment; doctor and admin states must sync | No transition enforcement or doctor actions | 5-status model, enforced in UI and rules, live sync, event history | ADM-08 to ADM-18, DR-03 to DR-15
I15 | High | Doctor closes ticket with amount paid to technician; denial/cancel handling | Not built | Mark as completed + amount + confirm; close on behalf; mandatory cancel reasons for doctor and admin | DR-03 to DR-14, ADM-10 to ADM-14
I16 | High | Doctor needs future time slots (9-12, 2-5, 6-9) | Not built | Date + slot picker, future only, server-checked | SLT-01 to SLT-13
I17 | Medium | Fee text (Rs 0, free visit, inspection charges) is misleading | Static copy | Replace with 'free to use; pay technician directly' | BKG-29, UI-09
I18 | Medium | Fake technicians seeded from the app | Client seed routine | Remove; admin adds real technicians | ADT-03 to ADT-06
I19 | High | Debug build; dev/staging/prod configs; staging ribbon | Debug APK (~175 MB) | Flavors; signed release AAB; prod only on prod project | DEP-01 to DEP-12, SEC-12, UI-06
I20 | Medium | Scale to 1 lakh users | Streams of full collections | Pagination, aggregation, indexes, budgets, App Check | PERF-01 to PERF-08
I21 | Medium | Missing for store launch: account deletion, privacy policy, support number, crash reporting | Not present | Add Profile screen, links, Crashlytics, Remote Config min version | PRF-01, PRF-05, PRF-06, DEP-08, DEP-09
Causes come from reading the APK's embedded code and manifest; both uploaded APKs contain the same code. Confirm each on a running build.